TENDER BID SUBMISSION

Technical & Financial Bid

RfP No.  TENDER/EPC/2026-27/1BC3

Submission of Technical Qualification and Financial Bid in response to the Tender Document referenced as Rooftop Solar PV Power 2026 - complete scope of supply, installation, testing & commissioning on Turnkey EPC basis.

| SUBMITTED TO | The Concerned Tender Authority | DATE OF SUBMISSION | 01 May 2026 |
| --- | --- | --- | --- |
| SUBMITTED BY | AuraVolt EPC Solutions Pvt. Ltd., Jaipur, Rajasthan | BID REFERENCE | AVE/TENDER/2026/315A |
| AUTHORISED SIGNATORY | Mr. Arvind Mehta, Director (Technical) | DSC USED | Class-III DSC ¦ Token No. SIFY-2026-1BC-89D9 |
| EMD / BID SECURITY | INR 18,75,000/- ¦ BG No. SBI/JPR/BG/2026/1BC38 | TENDER FEE REF. | NEFT Ref. SBIN261BC389 ¦ INR 11,800/- (incl. GST) |
| BID VALIDITY | 180 days from Financial Bid opening (i.e., up to 28 October 2026) | TYPE OF BID | Two-Envelope: Technical Bid (Env. 1) + Financial Bid (Env. 2) |

Covering Letter

To,

The Concerned Tender Authority

As per the Request for Proposal document

Subject:  Submission of Technical and Financial Bid for RfP No. TENDER/EPC/2026-27/1BC3

Sir/Madam,

We, AuraVolt EPC Solutions Pvt. Ltd., having our registered office at Plot No. 22, Industrial Area Phase-III, Sitapura, Jaipur - 302 022, Rajasthan, India (CIN: U40100RJ2013PTC041287), hereby submit our Technical and Financial Bid in response to the above-referenced Request for Proposal for the complete scope of design, engineering, supply, installation, testing & commissioning on Turnkey EPC basis with comprehensive O&M as per the tender requirements.

We confirm that we have carefully read and understood all the terms, conditions, scope of work, eligibility criteria, and instructions contained in the tender document. We accept all the terms and conditions without any deviation, condition, or qualification, and undertake to execute the work in strict conformity with the requirements within the timelines specified.

We confirm that all information and documents submitted herewith are true, accurate, and complete to the best of our knowledge. We understand that any misrepresentation shall render this bid liable to rejection and may result in disqualification / blacklisting.

We enclose herewith the Earnest Money Deposit (INR 18,75,000/- | BG No. SBI/JPR/BG/2026/1BC38) and Tender Fee (NEFT Ref. SBIN261BC389 | INR 11,800/- (incl. GST)). We remain available for any clarification or pre-award discussions at your convenience.

Thanking you,

Yours faithfully,

| SIGNATURE ____________________________ Mr. Arvind Mehta Director (Technical) · AuraVolt EPC Solutions Pvt. Ltd. DIN 07412659 · 01 May 2026 · Jaipur, Rajasthan | COMPANY SEAL [OFFICIAL SEAL] |
| --- | --- |

ENVELOPE 1

Technical Bid

The Technical Bid is organised in the following sections matching the tender document checklist. All supporting documents are enclosed as referenced.

SECTION T-1

Bidder Profile and Legal Status

| COMPANY NAME | AuraVolt EPC Solutions Pvt. Ltd. |
| --- | --- |
| TYPE OF ENTITY | Private Limited Company (Companies Act 2013) |
| CIN | U40100RJ2013PTC041287 |
| DATE OF INCORPORATION | 08 May 2013 |
| PAN | AAJCA9876H |
| GSTIN | 08AAJCA9876H1ZK - Active |
| REGISTERED OFFICE | Plot No. 22, Industrial Area Phase-III, Sitapura, Jaipur - 302 022, Rajasthan, India |
| AUTHORISED CAPITAL | INR 5,00,00,000/- |
| PAID-UP CAPITAL | INR 3,75,00,000/- |
| NO. OF EMPLOYEES | 156 (as on 01 May 2026) |
| ISO CERTIFICATION | ISO 9001:2015 (Cert. No. QMS-2022-IN-05192, valid till Apr 2027) |

Enclosures T-1A to T-1E: Certificate of Incorporation, MOA & AOA, GST Registration, PAN Card, MCA Director Extract.

SECTION T-2

MNRE / Authority Empanelment

| EMPANELMENT AUTHORITY | Ministry of New and Renewable Energy (MNRE), Govt. of India |
| --- | --- |
| CATEGORY | Solar EPC Contractor / Channel Partner - Grid-Connected Rooftop |
| EMPANELMENT NO. | MNRE/ALMM/EPC/RAJ/2022/00891 (Valid 01 Apr 2022 - 31 Mar 2026) |
| STATE EMPANELMENT | RRECL/EMP/SOLAR/2021/0124 (Valid till 30 Jun 2025) |

SECTION T-3

Technical Experience - Completed Projects

The following grid-connected solar PV projects have been successfully commissioned by AuraVolt EPC Solutions Pvt. Ltd. in the last 7 financial years. Total commissioned capacity: 4.85 MWp.

| S.NO. | PROJECT / CLIENT | LOCATION | CAPACITY | TYPE | COD | CERT. REF. |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Rajasthan Housing Board - HQ Campus Solar Plant | Jaipur, RJ | 500 kWp | Grid-Connected Rooftop | 12 Sep 2019 | RHB/EE/COD/2019/041 |
| 2 | MNIT Jaipur - Academic Block Solar Installation | Jaipur, RJ | 300 kWp | Grid-Connected Rooftop | 22 Mar 2020 | MNIT/Solar/COD/2020/007 |
| 3 | AIIMS Jodhpur - Solar Rooftop Phase-I | Jodhpur, RJ | 650 kWp | Grid-Connected Rooftop | 08 Nov 2020 | AIIMS-J/COD/2020/018 |
| 4 | Bikaner Municipal Corporation - 12 Sites | Bikaner, RJ | 420 kWp (35 kWp x 12) | Grid-Connected Rooftop | 15 Jun 2021 | BMC/Solar/COD/2021/033 |
| 5 | RIICO Industrial Area - Neemrana Solar Park | Neemrana, RJ | 1,000 kWp (1 MWp) | Ground-Mounted Grid-Connected | 29 Jan 2022 | RIICO/Solar/COD/2022/005 |
| 6 | Rajasthan Police - 28 Police Stations Solar | Multi-district, RJ | 560 kWp (20 kWp x 28) | Grid-Connected Rooftop | 30 Sep 2022 | RPHQ/Solar/COD/2022/047 |
| 7 | SMS Medical College - Solar Rooftop | Jaipur, RJ | 420 kWp | Grid-Connected Rooftop | 14 Apr 2023 | SMS/Solar/COD/2023/012 |
| 8 | Rajasthan State Archives Building | Bikaner, RJ | 250 kWp | Grid-Connected Rooftop | 10 Nov 2023 | RSA/Solar/COD/2023/029 |
| 9 | District Collectorate Offices - 5 Locations | Ajmer / Kota / Sikar, RJ | 350 kWp (70 kWp x 5) | Grid-Connected Rooftop | 28 Mar 2024 | RRD/Solar/COD/2024/014 |
| 10 | Rajasthan Tourism Hotels - Solar Rooftop | Jaipur/Udaipur/Jodhpur, RJ | 400 kWp | Grid-Connected Rooftop | 22 Aug 2024 | RTDC/Solar/COD/2024/031 |

SECTION T-4

Financial Capacity

Audited financial statements are enclosed as Enclosures T-4A to T-4C. CA Certificate (UDIN: 25034571BAAAIY8921) enclosed as Enclosure T-4D.

| FINANCIAL YEAR | GROSS TURNOVER (INR) | NET PROFIT (INR) | NET WORTH (INR) |
| --- | --- | --- | --- |
| FY 2022-23 (Audited) | INR 6,84,32,500/- | INR 58,42,000/- | INR 2,84,17,000/- |
| FY 2023-24 (Audited) | INR 9,12,75,000/- | INR 87,63,000/- | INR 3,48,92,000/- |
| FY 2024-25 (Audited) | INR 11,45,60,000/- | INR 1,12,84,000/- | INR 4,41,22,000/- |
| 3-Year Average Turnover | INR 9,14,22,500/- | - | - |

| BANK | State Bank of India, Sitapura Industrial Branch (IFSC: SBIN0031245) |
| --- | --- |
| ACCOUNT NO. | 00000041287523XXX (CC Limit: INR 3.50 Crore) |
| SOLVENCY CERTIFICATE | SBI/JMB/SOL/2025/0044 dated 01 May 2026 |
| WORKING CAPITAL AVAILABLE | INR 2.75 Crore (confirmed by Bank Certificate - Enclosure T-4E) |

SECTION T-5

Key Personnel

| NAME | DESIGNATION | QUALIFICATION | ELECTRICAL SUPERVISOR LICENSE | EXPERIENCE |
| --- | --- | --- | --- | --- |
| Mr. Vikram Singh Rathore | Head - Electrical Works | B.E. (Electrical) University of Rajasthan, 2006 | RAJ-ES-2008-04712 (Valid till Dec 2026) | 18 Years |
| Mr. Suresh Chand Meena | Sr. Electrical Engineer | B.Tech (EE) RTU Kota, 2011 | RAJ-ES-2013-07831 (Valid till Sep 2025) | 13 Years |
| Ms. Anjali Gupta | Solar Design Engineer | B.E. (EE) BITS Pilani, 2015 | RAJ-ES-2017-11294 (Valid till Mar 2026) | 9 Years |

SECTION T-6

ALMM / Standards Compliance Undertaking

We, AuraVolt EPC Solutions Pvt. Ltd., hereby unconditionally confirm and undertake that: 1. All solar PV modules to be supplied and installed under this contract shall be sourced exclusively from manufacturers listed in MNRE's Approved List of Models and Manufacturers (ALMM) as on the date of procurement. 2. All modules shall carry valid BIS certification under IS 14286 and shall comply with IEC 61215 / IEC 61730 standards as on the date of installation. 3. We shall furnish documentary evidence of compliance (MNRE portal print, test certificates, and delivery invoices showing model numbers) to the Tender Authority before and after equipment supply. 4. We understand that use of non-compliant modules shall constitute a material breach of contract and the Tender Authority shall be entitled to reject the supply, levy penalties, and terminate the contract. Signed by: Mr. Arvind Mehta, Director (Technical) ¦ Date: 01 May 2026 ¦ Place: Jaipur, Rajasthan

SECTION T-7

Integrity Pact & Anti-Bribery Declaration

We, AuraVolt EPC Solutions Pvt. Ltd., acting through our duly authorised Director (Technical) Mr. Arvind Mehta, hereby solemnly declare and affirm that: 1. We have not offered, given, or promised any gift, payment, consideration, or benefit of any kind, directly or indirectly, to any officer or employee of the Tender Authority or any Government department in connection with this bid or any anticipated contract. 2. We have not colluded with any other bidder or person to fix bid prices or restrict competition in any manner. 3. We are not blacklisted, debarred, or under investigation by any Central or State Government department, PSU, or financial institution as on the date of this bid. 4. We acknowledge that the Tender Authority has the right to reject our bid and initiate legal proceedings if this declaration is found to be false at any stage.

SECTION T-8

Technical Approach and Methodology

AuraVolt EPC Solutions Pvt. Ltd. proposes to execute the project in the following structured phases:

| PHASE | ACTIVITY | TIMELINE (FROM LOA) | DELIVERABLE |
| --- | --- | --- | --- |
| Phase 1 (Days 1-30) | Site Survey, Structural Assessment, Shadow Analysis, Design Preparation and Submission | Design documents submitted by Day 30 | Site survey report, SLD, yield estimate, structural certificate per site |
| Phase 2 (Days 31-60) | Equipment Procurement, Vendor Finalization, Compliance verification, Factory inspection | PO to vendors by Day 40; Delivery begins Day 55 | Equipment list with make/model/datasheets |
| Phase 3 (Days 61-120) | Civil and Structural Works (MMS fabrication, cable tray, conduit, foundations) | Structural works complete by Day 120 | Weekly progress photo reports; structural certificate |
| Phase 4 (Days 121-155) | Electrical Works (DC and AC wiring, earthing, lightning protection, switchboard) | Electrical works complete by Day 150 | As-built SLD, DISCOM acknowledgement, completion certificate |
| Phase 5 (Days 156-175) | System Testing, Pre-Commissioning Checks, DISCOM inspection, Commissioning | COD target: Day 175 (5 days buffer) | Commissioning test reports, DISCOM approval letter |
| Phase 6 (Year 1-5) | Comprehensive O&M: 2 scheduled visits/year, remote monitoring, 48-hr fault response | Ongoing for 5 years from each site COD | Quarterly O&M reports; annual performance reports (CUF data) |

ENVELOPE 2

Financial Bid

Price Schedule / Bill of Quantities  ·  RfP No. TENDER/EPC/2026-27/1BC3  ·  Bid Ref. AVE/TENDER/2026/315A  ·  01 May 2026

This Financial Bid is submitted as required by the two-envelope system. The rates quoted below are all-inclusive covering the complete scope of supply, installation, testing, commissioning, and applicable taxes. No additional claim of any nature will be raised after award of the contract.

| # | DESCRIPTION | SPECIFICATIONS | BRAND / MAKE | QTY | UNIT | RATE (INR) | TOTAL (INR) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Solar PV Modules | Minimum 540 Wp per module, monocrystalline PERC or TOPCon, ≥21% efficiency, MNRE ALMM List-I, BIS IS 14286, 12-year product warranty, 25-year performance guarantee ≥80% rated power. | Waaree | 371 | nos | 16,200.00 | 60,10,200.00 |
| 2 | Grid-Tied Inverters | 3-phase 415V ±10%, ≥98% CEC weighted efficiency, IEC 62109-1/2 compliant, anti-islanding, FRT capability, DC arc-fault protection, MNRE type-test approved, PGVCL interconnection approved, 5-year on-site warranty. | Growatt | 1 | lot | 54,550.00 | 54,550.00 |
| 3 | Module Mounting Structure | Hot-dip galvanized mild steel IS 2062 Grade B, ≥85 micron zinc coating, fixed tilt optimized for Rajkot latitude, withstands 180 km/h wind per IS 875 Part-3, SS 304 hardware, licensed structural engineer certificate required. | Schletter India / Kseng Solar | 1 | lot | 1,950.00 | 1,950.00 |
| 4 | Lightning Protection System | IS/IEC 62305 compliant, ESE type or conventional Franklin rod per risk analysis, complete bonding of all metallic structures to main earth bus. | Indelec / Aplicaciones Tecnologicas | 1 | lot | 32,500.00 | 32,500.00 |
| Subtotal (Basic Value) |  |  |  |  |  |  | 60,99,200.00 |
| GST @ 18% |  |  |  |  |  |  | 10,97,856.00 |
| Grand Total (incl. all taxes & GST) |  |  |  |  |  |  | 71,97,056.00 |

Amount in words   Seventy One Lakh Ninety Seven Thousand Fifty Six Rupees Only

NOTES

1.  The quoted rates are firm and fixed for the entire contract period. No price escalation, variation, or additional claim of any nature shall be raised after award of contract.

2.  The above rates are inclusive of all applicable taxes, duties, levies, and GST as on the date of bid. Any future change in GST rate shall be dealt with as per Government of India notification.

3.  The rates are inclusive of design, engineering, supply, installation, testing, commissioning, freight, insurance, and statutory charges as applicable to the scope of work.

4.  This Financial Bid is valid for 180 days from Financial Bid opening (i.e., up to 28 October 2026).

5.  Any conditional bid or bid with deviations is liable for rejection at the sole discretion of the Tender Authority.

ANNEXURE

Declaration by Authorised Signatory

I, Mr. Arvind Mehta, Director (Technical) of AuraVolt EPC Solutions Pvt. Ltd., being duly authorised by the Board of Directors vide Board Resolution dated 24 April 2026, hereby declare that all information, documents, and statements submitted in this bid are true, accurate, and complete to the best of my knowledge and belief. I confirm that the company has not been blacklisted by any Government authority and that we accept all terms and conditions of the tender document without any deviation. I understand that any false declaration shall render this bid liable to rejection and may result in disqualification and/or blacklisting of the company. I further confirm that the rates quoted in the Financial Bid (Envelope 2) are firm and fixed for the entire contract period and that we shall execute the awarded scope in strict compliance with the technical specifications, quality standards, and timelines stipulated in the tender document.

| SIGNATURE ____________________________ Mr. Arvind Mehta Director (Technical) · AuraVolt EPC Solutions Pvt. Ltd. DIN 07412659 · 01 May 2026 · Jaipur, Rajasthan | COMPANY SEAL [OFFICIAL SEAL] |
| --- | --- |

ANNEXURE

Enclosures Summary

•  T-1A to T-1E: Legal Documents (CoI, MoA & AoA, GST Cert., PAN, MCA extract)

•  T-2A to T-2B: MNRE & Empanelment Certificates

•  T-3A to T-3J: COD Certificates of 10 completed projects

•  T-4A to T-4E: Audited Financial Statements & Bank Solvency

•  T-5A to T-5C: Key Personnel CVs, Licenses, PF Statements

•  T-6: ALMM Compliance Undertaking

•  T-7: Integrity Pact & Anti-Bribery Declaration

•  T-8: Power of Attorney for Authorised Signatory

•  T-9: EMD Bank Guarantee (original)

•  T-10: Tender Fee NEFT Receipt